## R50
Task | Estimate Start Time | Estimate Completion Time | Estimated Duration | Reboot? | Actual Start Time | Actual Completion time | Actual Duration | Potential Issues?
Start "Migration" upgrade | 13:10 | 17:10 | 4:00 | X | 13:10 | 17:40 | 4:30
Apply AIX 5.1 ML1 | 17:10 | 17:55 | 0:45 | X | 17:40 | 18:10 | 0:30
Receive signoff from SAP/DB2 team

## SAPBO
| Task | Estimate Start Time | Estimate Completion Time | Estimated Duration | Reboot? | Actual Start Time | Actual Completion time | Actual Duration | Potential Issues?
| Shutdown SAP/DVB | 8:00 | 8:05 | 0:05 |  | 7:00 | 7:15 | 0:15
| Perform a mksysb | 8:05 | 8:30 | 0:25 |  | 7:50 | 8:07 | 0:17
| Perform second mksysb | 8:30 | 8:55 | 0:25 |  | 8:12 | 8:28 | 0:16
| Perform microcode upgrade | 8:55 | 9:25 | 0:30 | X | 8:30 | 8:50 | 0:20 | 1
| Unmount all non-rootvg filesystems | 9:25 | 9:35 | 0:10 |  | 8:51 | 8:52 | 0:01
| Start "Migration" upgrade | 9:35 | 12:35 | 3:00 | X | 8:55 | 11:20 | 2:25 | 2
| Perform first AIX 5.2 mksysb | 12:35 | 13:00 | 0:25 |  | 11:27 | 11:48 | 0:21
| Apply AIX 5.2 ML1 | 13:00 | 13:45 | 0:45 | X | N/A | N/A | N/A | 3
| Start SAP/DVB | 13:45 | 13:50 | 0:05 |  | N/A | N/A | N/A
| Perform second AIX 5.2 mksysb | 13:50 | 14:15 | 0:25 |  | N/A | N/A | N/A
| Receive signoff from SAP/DB2 team |  |  |  |  | N/A | N/A | N/A
1. The F50 requires 2 reboots for a microcode upgrade. This is because there is both system microcode and service processor microcode.
2. The Shark drivers and SDD were not affected by the upgrade
3. The ML1 level was applied with the base-level CD's at the time of "migration".

## SAPBWP
Task | Estimate Start Time | Estimate Completion Time | Estimated Duration | Reboot? | Actual Start Time | Actual Completion time | Actual Duration | Potential Issues?
Shutdown SAP/BWP | 8:00 | 8:05 | 0:05
Perform a mksysb | 8:05 | 8:30 | 0:25 |  | 8:04 | 8:13 | 0:09
Perform second mksysb | 8:30 | 8:55 | 0:25 |  | 8:14 | 8:21 | 0:07
Unmirror rootvg | 8:55 | 9:10 | 0:15 |  | 8:30 | 8:45 | 0:15
Perform microcode upgrade and boot right to install | 9:10 | 9:40 | 0:30 | X | 8:45 | 9:00 | 0:15
Unmount all non-rootvg filesystems | 9:40 | 9:50 | 0:10 |  |  |  | 0:00
Start "Migration" upgrade | 9:50 | 13:50 | 4:00 | X | 9:00 | 10:28 | 1:28
Perform first AIX 5.2 mksysb | 13:50 | 14:15 | 0:25 |  | 10:30 | 10:43 | 0:13
Re-mirror rootvg | 13:50 | 14:20 | 0:30 |  | 10:44 | 11:43 | 0:59
Start SAP/BWP | 14:20 | 14:25 | 0:05 |  | 11:45 | 11:48 | 0:03
Receive signoff from SAP/DB2 team |  |  |  |  | 11:48 | 11:48 | 0:00
After unmirroring rootvg, a "migratepv" was needed to clean up some mis-allocated logical volumes
back to hdisk0
CD #2 prompt at T + 0:46
CD #3 prompt at T + 0:49
CD #4 prompt at T + 0:55
CD #1 prompt at T + 0:57
Reboot at 10:19 AM
Ignore ESS configuration errors during migration
Re-mirror rootvg requires a change to rootvg quorum setting and therefore requires a reboot

## DV-QA
Task | Estimate Start Time | Estimate Completion Time | Estimated Duration | Reboot? | Actual Start Time | Actual Completion time | Actual Duration | Potential Issues?
Shutdown SAP/DV1 | 8:00 | 8:05 | 0:05
Shutdown SAP/QA1 | 8:05 | 8:10 | 0:05
Send PR1 offline | 8:10 | 8:15 | 0:05 |  | 8:10 | 8:11 | 0:01
Send BK's and/or DV's | 8:15 | 8:20 | 0:05 |  | 8:12 | 8:13 | 0:01
Perform a mksysb | 8:20 | 8:45 | 0:25 |  | 8:14 | 8:28 | 0:14
Perform second mksysb | 8:45 | 9:10 | 0:25 |  | 8:29 | 8:43 | 0:14
Perform microcode upgrade | 9:10 | 9:40 | 0:30 | X | 8:45 | 8:59 | 0:14 | X
Start "Migration" upgrade | 9:40 | 13:40 | 4:00 | X | 9:00 | 15:30 | 6:30 | 1
Perform first AIX 5.2 mksysb | 13:40 | 14:05 | 0:25 |  | 15:31 | 15:49 | 0:18
Apply AIX 5.2 ML1 | 14:05 | 14:50 | 0:45 | X
Receive BK's and/or DV's | 14:50 | 14:55 | 0:05 |  | 15:37 | 15:39 | 0:02
Bring PR1 online | 14:55 | 15:00 | 0:05 |  | 15:37 | 15:41 | 0:04
Send PR1 offline | 15:00 | 15:05 | 0:05
Send BK's and/or DV's | 15:05 | 15:10 | 0:05
Receive BK's and/or DV's on another SAP80i | 15:10 | 15:20 | 0:10
Send BK's and/or DV's from SAP80i | 15:20 | 15:25 | 0:05
Start SAP/DV1 | 15:25 | 15:30 | 0:05
Start SAP/QA1 | 15:30 | 15:35 | 0:05 |  | 15:51 | 15:52 | 0:01
Perform second AIX 5.2 mksysb | 15:35 | 16:00 | 0:25 |  | 15:51 | 15:52 | 0:01
Receive signoff from SAP/DB2 team
Issues/notes:
X - After migrocode update, boot directly to install. Do not boot into AIX.
Disk 2 prompt at T + 1:19
Disk 3 prompt at T + 1:27
Disk 4 prompt at T + 1:39
Disk 5 prompt at T + 1:52
Disk 6 prompt at T + 2:05
Finish at T + 2:17
Reboot at T + 3:15
1: During the install, the AIX hdisks may be renumbered. This will only be true for the install. When the system comes up, the hdisks will
revert to their original identifications.
1: System did not boot after install. See exceptions tab for this server, for exact problems.

## DV-QA Exceptions
When the migration install finished, the system rebooted and went to "AIX is starting". Then it gave me a nice empty stare. For a long time.
No disk activity, so I rebooted again (after about 30-minutes). Same thing.
So I called IBM and here is what we found. (PMR 89137-122)
There exists, under certain conditions, a situation where a migrated server will not reboot after a migration.
Yup - the install will fail. You'll need to reload a mksysb and start again. The fix ?
Unmirror rootvg first.
The AIX 5.2 migration MIGHT die if you migrate a mirrored rootvg. The developers at IBM are not yet sure what the problem is.
They are considering writing this into the migration guide at this point.
Symptoms: | System will not boot
Fixes: | Run fsck, synclvodm, etc - none will fix the problem. Nothing will work, even though the commands run fine (and might even fix something)
Fortunately, in my case, I was not affected by this particular bug. In my case however, here is what happened to me:
On the /SPOT, /etc/filesystems had no entry for "/tmp" in it, so I had to "grep -p" and "sed" to create a new entry and append it to /etc/filesystems
Then, I could run "fsck" on /tmp. At this point, we were not sure if my system had "the bug" or not. So watch for the missing "/tmp".
My bos.mp was still 4.3.3.75 and did not migrate.
My devices.ssa.disk.rte was still 4.3.3.x and did not migrate.
Trying to install the filesets in "recovery" mode failed because the script "/usr/lib/instl/rminstal" failed. We placed an "exit 0" in that script and the install worked fine.
Once we set the bootlist and fixed the above problems, the system booted fine.

## PR1
Task | Estimate Start Time | Estimate Completion Time | Estimated Duration | Reboot? | Actual Start Time | Actual Completion time | Actual Duration | Potential Issues?
Shutdown SAP/PR1 | 8:00 | 8:05 | 0:05 |  | N/A | N/A | N/A
Send BK's and/or DV's | 8:05 | 8:10 | 0:05 |  | 8:03 | 8:03 | 0:00
Perform first mksysb | 8:10 | 8:35 | 0:25 |  | 8:03 | 8:15 | 0:12
Perform second mksysb | 8:35 | 9:00 | 0:25 |  | 8:15 | 8:25 | 0:10
De-install PSSP and other software | 9:00 | 10:00 | 1:00 |  | 8:29 | 8:40 | 0:11 | 1,2,X
Unmirror rootvg | 10:00 | 10:45 | 0:45 |  | 8:38 | 8:42 | 0:04 | 4,6
Perform microcode upgrade and boot right to install | 10:45 | 12:15 | 1:30 | X | 8:45 | 9:15 | 0:30
Start "Migration" upgrade | 12:15 | 17:45 | 5:30 | X | 9:28 | 12:14 | 2:46 | 5
Perform first AIX 5.2 mksysb | 17:45 | 18:10 | 0:25 |  | 12:59 | 13:11 | 0:12
Apply additional AIX 5.2 patches needed | 17:45 | 18:45 | 1:00 | X | N/A | N/A | N/A | 3
Re-mirror rootvg | 18:10 | 19:55 | 1:45 |  | 12:40 | 12:55 | 0:15
Receive BK's and/or DV's | 19:55 | 20:00 | 0:05 |  | N/A | N/A | N/A
Mount all PR1 filesystems | 20:00 | 20:10 | 0:10 |  | N/A | N/A | N/A
Start SAP/DB2 | 20:10 | 20:25 | 0:15 |  | N/A | N/A | N/A
Perform the following on sap1g: |  |  |  |  | N/A | N/A | N/A
Perform first mksysb | 8:00 | 8:25 | 0:25 |  | 8:15 | 8:25 | 0:10
Perform second mksysb | 8:25 | 8:50 | 0:25 |  | 8:26 | 8:37 | 0:11
Unmirror rootvg | 8:50 | 9:35 | 0:45 |  | 8:43 | 8:45 | 0:02 | 4
Perform microcode upgrade and boot right to install | 9:35 | 10:20 | 0:45 | X | 7:58 | 8:15 | 0:17
Start "Migration" upgrade | 10:20 | 13:20 | 3:00 | X | 8:48 | 9:58 | 1:10
Perform first AIX 5.2 mksysb | 13:20 | 13:45 | 0:25 |  | 10:39 | 10:52 | 0:13
Re-mirror rootvg | 13:20 | 14:50 | 1:30 |  | 10:11 | 10:32 | 0:21
Mount SAP80i SAP NFS filesystems | 14:50 | 14:55 | 0:05 |  | N/A | N/A | N/A
Contact DB2/SAP support for testing | 20:25 | 20:55 | 0:30 |  | 13:15 | 13:16 | 0:01
Receive signoff from SAP/DB2 team |  |  |  |  | N/A | N/A | N/A
Issues:
1. Will need to remove node65 from the SP complex on SAPCWS (spdelnode & spdelframe)
2. /usr/local/bin is exported everywhere and needs to be unmounted on the clients
All SAP NFS filesystems need to be unmounted on the APP servers
3. If no problems were found on the DV1/QA1 AIX upgrade, then there might not be any additional patches required
X. Deinstall PSSP, *ATM*, *GXT*, *sna*, *Graphics*, *tsm*, *mca* and less common "*terminfo*" files
4. After unmirroring rootvg, a "migratepv" may need to be done to clean up mis-allocated partitions
5. During the migration, when the system gets close to finishing, some ESS configuration errors may come up. Ignore them
6. Take an optional mksysb at this point